## Cover
Title | Project Crystal - JV Day 1 Readiness Plan
Description | All actions required to achieve JV Day-1 operational readiness
Date | 2026-03-02

## Summary
REQUIREMENTS BY OWNER | 117 | 4 | 89 | 24 | 0 | REQUIREMENTS BY CATEGORY | 119 | 4 | 91 | 24 | 0
Owner | Total | Completed | Not started | On-track | Delayed | Workstream | Total | Completed | Not started | On-track | Delayed
Hassen Moolla | 16 | 1 | 9 | 6 | 0 | Budget and BP | 9 | 1 | 4 | 4 | 0
Muddassar Khan | 14 | 2 | 5 | 7 | 0 | TSA | 6 | 1 | 4 | 1 | 0
Ramesh Murugesan | 13 | 0 | 12 | 1 | 0 | GSA | 6 | 0 | 4 | 2 | 0
Mawiyah Alqaed | 11 | 0 | 9 | 2 | 0 | DoA | 3 | 0 | 1 | 2 | 0
Aseel Alnafea | 8 | 0 | 7 | 1 | 0 | Secondment | 4 | 0 | 2 | 2 | 0
Rene Thumbran | 7 | 0 | 5 | 2 | 0 | SHA documentation | 9 | 0 | 1 | 8 | 0
Mohammed Al-Hamed | 6 | 0 | 4 | 2 | 0 | Corporate approval | 9 | 2 | 5 | 2 | 0
Faraj Al Dossary | 6 | 0 | 6 | 0 | 0 | Governance | 20 | 0 | 18 | 2 | 0
Omar Jabart | 6 | 0 | 4 | 2 | 0 | Legal | 6 | 0 | 6 | 0 | 0
Abdulrahman Abdullah Al-zahrani | 4 | 0 | 4 | 0 | 0 | GR | 4 | 0 | 4 | 0 | 0
Fathima Mahomed | 4 | 0 | 4 | 0 | 0 | HR | 6 | 0 | 6 | 0 | 0
Muddassar/Mohammed | 3 | 0 | 3 | 0 | 0 | HSSE | 6 | 0 | 6 | 0 | 0
Susan Parker | 3 | 0 | 3 | 0 | 0 | Finance | 10 | 0 | 10 | 0 | 0
Owen Hatton | 2 | 1 | 0 | 1 | 0 | IT | 13 | 0 | 12 | 1 | 0
Muddassar/Nuaim/Aseel Alnafea | 0 | 0 | 0 | 0 | 0 | Procurement | 4 | 0 | 4 | 0 | 0
Maaden and Aramco CEOs | 2 | 0 | 2 | 0 | 0 | Comms | 3 | 0 | 3 | 0 | 0
Abdullah Alzamil | 2 | 0 | 2 | 0 | 0 | Facilities | 1 | 0 | 1 | 0 | 0
Karim Mehboob | 2 | 0 | 2 | 0 | 0
Marwan Sutan | 2 | 0 | 2 | 0 | 0
Ramesh / Alex | 0 | 0 | 0 | 0 | 0
Aramco | 2 | 0 | 2 | 0 | 0
AshLaw | 1 | 0 | 1 | 0 | 0
Raud Alsuwailem | 1 | 0 | 1 | 0 | 0
Governance Dept | 1 | 0 | 1 | 0 | 0
Raoof Madathil | 1 | 0 | 1 | 0 | 0

## JV Readiness Plan
PROJECT CRYSTAL - JV DAY-1 READINESS PLAN | [6 empty] | Day-1 target date | 2026-08-31
Workstream | Category | Requirement | Action | Owner | Status | Start date | Duration | End date | Target Completion (%) | Actual Completion (%)
| Budget and Business Plan |  |  |  |  | 2026-02-01 | 58 | 2026-03-31
SHA | Budget and BP | Budget & BP Roles & Data Sources | Clarify roles and responsibilities across Maaden finance and technical teams. Define who provides what, sources of information, and internal points of contact for each workstream. | Hassen Moolla | Completed | 2026-02-01 | 14 | 2026-02-15 | 100% | 100%
SHA | Budget and BP | Budget and BP Inputs & Assumptions | Identify the full list of inputs and assumptions required to build the model. Define sources and providers for each item, and set deadlines for delivery. | Hassen Moolla | On-track | 2026-02-15 | 18 | 2026-03-05 | 83.33% | 80%
SHA | Budget and BP | 5-Year Exploration Plan | Develop 5-year Exploration Plan (2026-2030) | Owen Hatton | On-track | 2026-02-15 | 18 | 2026-03-05 | 83.33% | 80%
SHA | Budget and BP | JV Day-1 Org Chart | Finalize the Day-1 organization structure (confirm minimal technical staff requirements, including HSSE) | Mohammed Al-Hamed | On-track | 2026-02-18 | 14 | 2026-03-04 | 85.71% | 50%
SHA | Budget and BP | Build Draft BP Model | Construct the financial and operational model based on the defined inputs, assumptions, and agreed structure. Ensure formulas are robust and the model is auditable. | Hassen Moolla | On-track | 2026-03-05 | 7 | 2026-03-12 | 0% | 0%
SHA | Budget and BP | Validate BP with Key Maaden Stakeholders | Present the draft model and BP outputs to key Maaden stakeholders (technical and finance) for review. Incorporate feedback and resolve any open items. | Hassen Moolla | Not Started | 2026-03-12 | 3 | 2026-03-15 | 0% | 0%
SHA | Budget and BP | Package BP into Final Deliverable | Define format/templates and develop final deliverables | Hassen Moolla | Not Started | 2026-03-15 | 7 | 2026-03-22 | 0% | 0%
SHA | Budget and BP | BP Final Deliverable validation | Validate final deliverables | Mohammed Al-Hamed | Not Started | 2026-03-22 | 2 | 2026-03-24 | 0% | 0%
SHA | Budget and BP | Aramco Feedback on BP & Update | Share the finalized BP with Aramco for review. Collect feedback, incorporate agreed changes, and lock the final version for approval | Mohammed Al-Hamed | Not Started | 2026-03-24 | 7 | 2026-03-31 | 0% | 0%
| TSA |  |  |  |  | 2026-02-01 | 66 | 2026-04-08
SHA | TSA | TSA Technical Services Catalogue | Develop the catalogue of technical services to be provided by Maaden to the JV under the TSA, identify what services are to be provided by 3d parties | Owen Hatton | Completed | 2026-02-01 | 11 | 2026-02-12 | 100% | 100%
SHA | TSA | TSA Charge-out Rate Methodology | Define the pricing methodology: establish the approach and basis for pricing each category of services (e.g., cost-plus, market benchmark, fixed fee) | Hassen Moolla | On-track | 2026-02-12 | 24 | 2026-03-08 | 75% | 100%
SHA | TSA | TSA Charge-out Rates Determination | Apply the agreed pricing methodology to determine the applicable rates for each service in the catalogue | Hassen Moolla | Not Started | 2026-03-08 | 7 | 2026-03-15 | 0% | 0%
SHA | TSA | TSA Governance structure | Define TSA governance structure and process: how TSA services are requested, approved, monitored, billed, paid, accounted (TSA management process) | Muddassar | Not Started | 2026-03-04 | 14 | 2026-03-18 | 0% | 0%
SHA | TSA | TSA Legal framework | Finalize the TSA legal framework: draft and agree on the legal terms and conditions governing the provision of services, including scope, performance standards, liability, and termination provisions | Aseel Alnafea | Not Started | 2026-03-18 | 14 | 2026-04-01 | 0% | 0%
SHA | TSA | Aramco Feedback on TSA & Update | Share the finalized TSA version with Aramco for review. Collect feedback, incorporate agreed changes, and lock the final version for approval. | Muddassar Khan | Not Started | 2026-04-01 | 7 | 2026-04-08 | 0% | 0%
| GSA |  |  |  |  | 2026-02-01 | 66 | 2026-04-08
SHA | GSA | GSA Catalogue of services | Develop the catalogue of services to be provided by Maaden to the JV under the GSA | Hassen Moolla | On-track | 2026-02-01 | 35 | 2026-03-08 | 82.86% | 75%
SHA | GSA | GSA Charge-out Rate Methodology | Define the pricing methodology: establish the approach and basis for pricing each category of services (e.g., cost-plus, market benchmark, fixed fee) | Hassen Moolla | On-track | 2026-02-16 | 24 | 2026-03-12 | 58.33% | 100%
SHA | GSA | GSA Charge-out Rates Determination | Apply the agreed pricing methodology to determine the applicable rates for each service in the catalogue | Hassen Moolla | Not Started | 2026-03-12 | 7 | 2026-03-19 | 0% | 0%
SHA | GSA | GSA Governance structure | Define GSA governance structure and process : how GSA services are requested, approved, monitored, billed, paid, accounted (GSA management process) | Muddassar | Not Started | 2026-03-04 | 14 | 2026-03-18 | 0% | 0%
SHA | GSA | GSA Legal framework | Finalize the GSA legal framework: draft and agree on the legal terms and conditions governing the provision of services, including scope, performance standards, liability, and termination provisions | Aseel Alnafea | Not Started | 2026-03-18 | 14 | 2026-04-01 | 0% | 0%
SHA | GSA | Aramco Feedback on GSA & Update | Share the finalized TSA version with Aramco for review. Collect feedback, incorporate agreed changes, and lock the final version for approval | Muddassar Khan | Not Started | 2026-04-01 | 7 | 2026-04-08 | 0% | 0%
| DoA |  |  |  |  | 2026-02-15 | 37 | 2026-03-24
SHA | DoA | Shareholders DoAs reference | Obtain reference governance framework, obtain Maaden's existing Authority Matrix and Aramco's governance frameworks as benchmarks for the JV | Mawiyah Alqaed | On-track | 2026-02-24 | 9 | 2026-03-05 | 66.67% | 80%
SHA | DoA | Complete Design of DoA (Shedule 15) | Design the multi-tiered financial approval matrix (incl governance and internal controls) : define approval tiers below Board thresholds across CAPEX, OPEX, contracts, procurement, HR, litigation, treasury, and asset management, aligned with SHA | Omar Jabart | On-track | 2026-02-15 | 30 | 2026-03-17 | 50% | 40%
SHA | DoA | Aramco Feedback on DoA & Update | Share the finalized DoA version with Aramco for review. Collect feedback, incorporate agreed changes, and lock the final version for approval | Muddassar/Mohammed | Not Started | 2026-03-17 | 7 | 2026-03-24 | 0% | 0%
| Secondment |  |  |  |  | 2026-02-01 | 62 | 2026-04-04
SHA | Secondment | Secondment framework | Develop secondment framework agreement (duration, cost basis, reporting lines, benefits) | Rene Thumbran | On-track | 2026-02-01 | 40 | 2026-03-13 | 72.5% | 60%
SHA | Secondment | Secondment Agreement Allocation Methodology | Define cost allocation methodology and determine cost rates for secondees | Rene Thumbran | On-track | 2026-02-02 | 40 | 2026-03-14 | 70% | 60%
SHA | Secondment | JV Secondment Agreement draft | Draft JV secondment agreement | Aseel Alnafea | Not Started | 2026-03-14 | 14 | 2026-03-28 | 0% | 0%
SHA | Secondment | Aramco Feedback on Secondment Agreement & Update | Share the finalized Secondment Agreement with Aramco for review. Collect feedback, incorporate agreed changes, and lock the final version for approval | Muddassar/Mohammed | Not Started | 2026-03-28 | 7 | 2026-04-04 | 0% | 0%
| SHA documentation |  |  |  |  | 2026-02-19 | 62 | 2026-04-22
SHA | SHA documentation | SHA Sch.10 Guarantee for Permitted Transfers | Agree Form of Guarantee for Permitted Transfers (Schedule 10) | Muddassar Khan | On-track | 2026-02-19 | 20 | 2026-03-11 | 55% | 25%
SHA | SHA documentation | SHA Sch.11 Form of the Agreement | Finalize Form of Shareholder Services Agreement (Schedule 11) | Muddassar Khan | On-track | 2026-02-19 | 20 | 2026-03-11 | 55% | 25%
SHA | SHA documentation | SHA Sch.16 Economical assumptions | Agree economic assumptions for technical studies (Schedule 16) - confirm applicability for Hard-Rock Exploration phase | Muddassar Khan | On-track | 2026-02-19 | 20 | 2026-03-11 | 55% | 25%
SHA | SHA documentation | SHA Sch.13 Competing business disclosure | Complete existing competing businesses disclosure (Schedule 13) (action also required for aramco) | Aseel Alnafea | On-track | 2026-02-24 | 14 | 2026-03-10 | 42.86% | 25%
SHA | SHA documentation | SHA Sch.14 Funding Notices | Develop Form of Funding Notices, and standard Funding Request Notice template (Schedule 14) | Hassen Moolla | On-track | 2026-02-19 | 14 | 2026-03-05 | 78.57% | 25%
SHA | SHA documentation | SHA Sch.2 Area of Interest and Transition Zone | Provide all Area of Interest and Transition Zone maps and coordinates (Schedule 2) | Mohammed Al-Hamed | On-track | 2026-02-19 | 14 | 2026-03-05 | 78.57% | 25%
SHA | SHA documentation | Exploration License Assignment Agreeement | Finalize Exploration License Assignment Agreeement | Muddassar Khan | On-track | 2026-02-19 | 42 | 2026-04-02 | 26.19% | 25%
SHA | SHA documentation | Exploration Services Agreement | Finalize Exploration Services Agreement | Muddassar Khan | On-track | 2026-02-19 | 42 | 2026-04-02 | 26.19% | 25%
SHA | SHA documentation | Aramco Feedback on SHA pack & Update | Share the final SHA documentation with Aramco for review. Collect feedback, incorporate agreed changes, and lock the final version for approval | Muddassar/Mohammed | Not Started | 2026-04-02 | 20 | 2026-04-22 | 0% | 0%
| Corporate approval |  |  |  |  | 2026-02-08 | 100 | 2026-05-19
SHA | Corporate approval | Maaden IC | Prepare material and obtain approval at Maaden Investment Committee meeting | Muddassar Khan | Completed | 2026-02-08 | 1 | 2026-02-09 | 100% | 100%
SHA | Corporate approval | Maaden ExCom | Prepare material and obtain approval at Maaden Excom meeting (Feb 17) | Muddassar Khan | Completed | 2026-02-17 | 1 | 2026-02-18 | 100% | 100%
SHA | Corporate approval | Maaden BoD | Prepare material and obtain approval at BoD meeting (Mar 5) | Muddassar Khan | Not Started | 2026-03-05 | 1 | 2026-03-06 | 0% | 0%
SHA | Corporate approval | 365-Day Implementation Plan Draft | Draft 365 Day Implementation Plan | Muddassar Khan | On-track | 2026-02-23 | 14 | 2026-03-09 | 50% | 20%
SHA | Corporate approval | 365-Day Implementation Plan (Final) | Share the finalized Plan with Aramco for review. Collect feedback, incorporate agreed changes, and lock the final version for approval | Muddassar Khan | Not Started | 2026-03-09 | 7 | 2026-03-16 | 0% | 0%
SHA | Corporate approval | 5-year Implementation Plan Draft | Draft JV Long-term Implementation Plan (key milestones) | Muddassar Khan | On-track | 2026-02-23 | 14 | 2026-03-09 | 50% | 20%
SHA | Corporate approval | 5-year Implementation Plan (Final) | Share the finalized Plan with Aramco for review. Collect feedback, incorporate agreed changes, and lock the final version for approval | Muddassar Khan | Not Started | 2026-03-09 | 7 | 2026-03-16 | 0% | 0%
SHA | Corporate approval | Board of Directors Aramco | Obtain approval at BoD meeting (mid-May) | Aramco | Not Started | 2026-05-13 | 1 | 2026-05-14 | 0% | 0%
SHA | Corporate approval | SHA signed by both Shareholders | Sign Shareholder Agreement | Maaden and Aramco CEOs | Not Started | 2026-05-14 | 5 | 2026-05-19 | 0% | 0%
| Entity Formation |  |  |  |  | 2026-03-01 | 148 | 2026-07-27
Entity Formation | Governance | Power of Attorney (PoA) | Issue legalized power of attorney authorizing Kingdom representatives before MOC and SBC (action also required for Aramco) | Omar Jabart | On-track | 2026-03-01 | 14 | 2026-03-15 | 7.143% | 0%
Entity Formation | Governance | Trade name reservation | Submit reservation of Trade name with Saudi Business Center (SBC), and obtain name approval from MOC | AshLaw | Not Started | 2026-03-15 | 7 | 2026-03-22 | 0% | 0%
Entity Formation | Governance | Constitutional documents | Gather constitutional documents and Financial Statements (e.g., certificate of incorporation and articles (or equivalent) and audited financial statements of each Shareholder | Mawiyah Alqaed | Not Started | 2026-03-15 | 14 | 2026-03-29 | 0% | 0%
Entity Formation | Governance | Initial Board remuneration | Define initial remuneration for Board Memebrs (action also required for Aramco) | Mawiyah Alqaed | On-track | 2026-03-01 | 14 | 2026-03-15 | 7.143% | 0%
Entity Formation | Governance | Board members nomination | Both shareholders nominate board members | Maaden and Aramco CEOs | Not Started | 2026-04-02 | 7 | 2026-04-09 | 0% | 0%
Entity Formation | Governance | Board members’ and GM information | Gather - from each board member and GM - a copy of passport/ID and contact information for MoC (action also required for Aramco) | Mawiyah Alqaed | Not Started | 2026-04-02 | 14 | 2026-04-16 | 0% | 0%
Entity Formation | Governance | Details of the ultimate beneficiary(ies) for MOC | Gather information of the ultimate beneficiaries for Ministry of Commerce | Mawiyah Alqaed | Not Started | 2026-04-30 | 14 | 2026-05-14 | 0% | 0%
Entity Formation | Governance | Board members/GM appointment consent | Board members and GM to approve their appointment - completed via Absher digital system (action also required for Aramco) | Mawiyah Alqaed | Not Started | 2026-04-02 | 14 | 2026-04-16 | 0% | 0%
Entity Formation | Legal | GAC no-notification application form | Prepare GAC no-notification application form to be submitted to the GAC | Aseel Alnafea | Not Started | 2026-04-15 | 7 | 2026-04-22 | 0% | 0%
Entity Formation | Legal | GAC no-notification economic report | Submit GAC no-notification economic report | Aseel Alnafea | Not Started | 2026-04-15 | 7 | 2026-04-22 | 0% | 0%
Entity Formation | Legal | GAC approval | Apply for and receive all required antitrust approvals (including GAC confirmation of non-applicability) | Aseel Alnafea | Not Started | 2026-05-19 | 60 | 2026-07-18 | 0% | 0%
Entity Formation | Governance | Board appointment Shareholders resolutions | Each Shareholder formally approves the appointment of their nominated Directors (action also required for Aramco) | Mawiyah Alqaed | Not Started | 2026-04-02 | 14 | 2026-04-16 | 0% | 0%
Entity Formation | Governance | AoA drafting | Draft AoA incorporating SHA terms and get shareholders approval | Omar Jabart | Not Started | 2026-04-15 | 21 | 2026-05-06 | 0% | 0%
Entity Formation | Governance | AoA approval | Submit AoA through SBC Portal (MOC) for MOC approval | Omar Jabart | Not Started | 2026-05-06 | 21 | 2026-05-27 | 0% | 0%
Entity Formation | Legal | AoA signing | Sign AoA before MOC/SBC official (via SBC portal) (with participation of Aramco) | Aseel Alnafea | Not Started | 2026-07-18 | 1 | 2026-07-19 | 0% | 0%
Entity Formation | Governance | AoA issuing | Complete payment of the MOC application and publication fees, Deliver Articles of Association issued electronically via the SBC portal | Mawiyah Alqaed | Not Started | 2026-07-19 | 2 | 2026-07-21 | 0% | 0%
Entity Formation | Governance | Maaden Board Members Registration with MOC | Formally register all Maaden directors with MOC | Omar Jabart | Not Started | 2026-07-21 | 3 | 2026-07-24 | 0% | 0%
Entity Formation | Governance | Aramco Board Members Registration with MOC | Formally register all Aramco directors with MOC | Aramco | Not Started | 2026-07-21 | 3 | 2026-07-24 | 0% | 0%
Entity Formation | Governance | Commercial Registration (CR) | Obtain CR from Ministry of Commerce | Omar Jabart | Not Started | 2026-07-24 | 3 | 2026-07-27 | 0% | 0%
| Post-formation registration |  |  |  |  | 2026-07-27 | 14 | 2026-08-10
Post-formation registration | GR | Chamber of Commerce registration | Register with local Chamber of Commerce | Abdulrahman Abdullah Al-zahrani | Not Started | 2026-07-27 | 7 | 2026-08-03 | 0% | 0%
Post-formation registration | Legal | ZAKAT, TAX and Customs registration | Register with the ZAKAT, Tax and Customs Authority | Abdullah Alzamil | Not Started | 2026-07-27 | 7 | 2026-08-03 | 0% | 0%
Post-formation registration | Legal | VAT registration | Register for VAT with ZATCA | Abdullah Alzamil | Not Started | 2026-07-27 | 14 | 2026-08-10 | 0% | 0%
Post-formation registration | GR | GOSI registration | Register with General Organization for Social Insurance (GOSI) | Abdulrahman Abdullah Al-zahrani | Not Started | 2026-07-27 | 7 | 2026-08-03 | 0% | 0%
Post-formation registration | HR | MHRSD registration | Register with Ministry of Human Resources (MHRSD) | Rene Thumbran | Not Started | 2026-07-27 | 7 | 2026-08-03 | 0% | 0%
Post-formation registration | GR | Saudi Post Registration | Registration with the Saudi Post Office | Abdulrahman Abdullah Al-zahrani | Not Started | 2026-07-27 | 7 | 2026-08-03 | 0% | 0%
Post-formation registration | GR | Municipality License | Obtain a municipality License from Ministry of Municipal and Rural Affairs | Abdulrahman Abdullah Al-zahrani | Not Started | 2026-07-27 | 14 | 2026-08-10 | 0% | 0%
Post-formation registration | HR | Nitaqat classification | Obtain initial Saudization classification | Rene Thumbran | Not Started | 2026-07-27 | 14 | 2026-08-10 | 0% | 0%
Post-formation registration | HSSE | Civil Defence Certificate | Obtain a Civil Defence Certificate, as necessary | Faraj Al Dossary | Not Started | 2026-07-27 | 14 | 2026-08-10 | 0% | 0%
| Corporate Governance Setup |  |  |  |  | 2026-05-19 | 97 | 2026-08-24
Corporate Governance Setup | Governance | BoD Charter | Develop BoD Charter (incl. board composition, committees, authority matrices, voting & veto rights, exec management governance, performance assessment) | Mawiyah Alqaed | Not Started | 2026-05-19 | 21 | 2026-06-09 | 0% | 0%
Corporate Governance Setup | Governance | Board of Directors on-boarding | Prepare on-boarding documentation for JV Board of Directors | Raud Alsuwailem | Not Started | 2026-06-09 | 14 | 2026-06-23 | 0% | 0%
Corporate Governance Setup | Governance | Shareholders Resolution (General Assembly) | Shareholders undertake all resolutions (by unanimous written circular resolution or General Assembly) required to give effect to SHA terms (action also required for Aramco) | Mawiyah Alqaed | Not Started | 2026-07-20 | 7 | 2026-07-27 | 0% | 0%
Corporate Governance Setup | Governance | Inaugural Board meeting | Prepare and conduct first Board meeting and approve foundational resolutions (e.g. company accession) | Mawiyah Alqaed | Not Started | 2026-07-27 | 7 | 2026-08-03 | 0% | 0%
Corporate Governance Setup | Governance | Executive management transition plan | Develop executive management transition support plan to support smooth handover from setup phase to operational governance | Governance dept | Not Started | 2026-08-03 | 21 | 2026-08-24 | 0% | 0%
| Operational readiness |  |  |  |  | 2026-02-17 | 195 | 2026-08-31
Operational readiness | Finance | Financial Policy Manual | Identify policy required for JV to operate and develop Finance Policy Manual | Hassen Moolla | Not Started | 2026-04-05 | 21 | 2026-04-26 | 0% | 0%
Operational readiness | Finance | JV Financial KPIs | Define Finance KPIs & monitor main performance measurement indicators | Hassen Moolla | Not Started | 2026-04-05 | 14 | 2026-04-19 | 0% | 0%
Operational readiness | Finance | Financial reporting templates | Define standard monthly /quarterly financial report templates (including BoD, shareholders) and align with Aramco CFO | Hassen Moolla | Not Started | 2026-04-19 | 14 | 2026-05-03 | 0% | 0%
Operational readiness | Finance | Auditing principles | Agree on external auditor selection criteria and process, define audit committee role, and confirm audit timeline for Year 1 | Karim Mehboob | Not Started | 2026-04-05 | 14 | 2026-04-19 | 0% | 0%
Operational readiness | Finance | External auditor selection | Identify and shortlist external auditors, define scope of audit, present recommendation to Board for approval at inaugural meeting | Karim Mehboob | Not Started | 2026-04-19 | 60 | 2026-06-18 | 0% | 0%
Operational readiness | Finance | Initial Insurance protection | Identify and procure insurance coverage for the JV (D&O liability, general liability, professional indemnity, property/equipment insurance for exploration activities) | Hassen Moolla | Not Started | 2026-06-10 | 14 | 2026-06-24 | 0% | 0%
Operational readiness | Finance | Corporate bank accounts | Open bank accounts | Marwan Sutan | Not Started | 2026-07-27 | 21 | 2026-08-17 | 0% | 0%
Operational readiness | Finance | Bank signatory authorization | Register authorized signatories | Marwan Sutan | Not Started | 2026-07-27 | 7 | 2026-08-03 | 0% | 0%
Operational readiness | Finance | Cash call schedule Year 1 | Define quarterly funding schedule | Hassen Moolla | Not Started | 2026-03-15 | 7 | 2026-03-22 | 0% | 0%
Operational readiness | Finance | Initial capital contribution | Initial cash call from shareholders | Mohammed Al-Hamed | Not Started | 2026-08-17 | 14 | 2026-08-31 | 0% | 0%
Operational readiness | IT | IT Systems requirements | Identify all systems needed for JV | Ramesh Murugesan | On-track | 2026-02-17 | 14 | 2026-03-03 | 92.86% | 30%
Operational readiness | IT | IT Work scope | Scoping and requirement documentation | Ramesh Murugesan | Not Started | 2026-03-03 | 14 | 2026-03-17 | 0% | 0%
Operational readiness | IT | Shareholders' IT Alignment | Prepare and conduct workshop with Aramco IT to showcase Maaden systems capabilities and agree on IT strategy | Ramesh Murugesan | Not Started | 2026-03-17 | 30 | 2026-04-16 | 0% | 0%
Operational readiness | IT | IT systems Implementation | Implement systems (configuration, training, testing, deployment) | Ramesh Murugesan | Not Started | 2026-03-17 | 90 | 2026-06-15 | 0% | 0%
Operational readiness | IT | IT Access Rights Assigned to JV Users | Grant relevant system access to end users | Ramesh Murugesan | Not Started | 2026-06-15 | 3 | 2026-06-18 | 0% | 0%
Operational readiness | IT | Chart of Accounts configuration | Load CoA in ERP | Ramesh Murugesan | Not Started | 2026-06-18 | 7 | 2026-06-25 | 0% | 0%
Operational readiness | IT | JV New IT Systems Subscriptions & Licences | Acquire / subscribe to systems needed for JV operations (not available through shareholders) | Ramesh Murugesan | Not Started | 2026-03-17 | 60 | 2026-05-16 | 0% | 0%
Operational readiness | IT | IT Systems training | Prepare and run training sessions with JV employees on relevant systems and processes | Ramesh Murugesan | Not Started | 2026-07-27 | 14 | 2026-08-10 | 0% | 0%
Operational readiness | IT | Cybersecurity training | Prepare and run cybersecurity training sessions with day-1 staff | Ramesh Murugesan | Not Started | 2026-07-27 | 14 | 2026-08-10 | 0% | 0%
Operational readiness | IT | JV Email & Account Setup | Register JV email domain (if any) and create email accounts for Day-1 staff | Ramesh Murugesan | Not Started | 2026-07-27 | 7 | 2026-08-03 | 0% | 0%
Operational readiness | IT | Laptops/computers | Provide laptops and mobile phones for day-1 staff | Ramesh Murugesan | Not Started | 2026-05-12 | 60 | 2026-07-11 | 0% | 0%
Operational readiness | IT | Network infrastructure setup | Set up network infrastructure and internet (switches, firewall, routers) | Ramesh Murugesan | Not Started | 2026-05-12 | 60 | 2026-07-11 | 0% | 0%
Operational readiness | IT | Aramco Data migration plan | Manage and oversee data migration plan for all relevant data | Ramesh Murugesan | Not Started | 2026-07-27 | 14 | 2026-08-10 | 0% | 0%
Operational readiness | Procurement | Maaden Contracts Capacity Review | Assess the capacity of Maaden's existing contracts against the JV's projected demand, based on the JV Technical Work Program | Fathima Mahomed | Not Started | 2026-03-05 | 21 | 2026-03-26 | 0% | 0%
Operational readiness | Procurement | JV Procurement Plan | Develop a Procurement Plan to cover scope not addressed by existing contracts, based on the outcomes of the Contract Capacity Review. | Fathima Mahomed | Not Started | 2026-03-26 | 21 | 2026-04-16 | 0% | 0%
Operational readiness | Procurement | Procurement Demand Assessment | Estimate procurement activity volumes and define resource requirements to support JV demand | Fathima Mahomed | Not Started | 2026-04-16 | 14 | 2026-04-30 | 0% | 0%
Operational readiness | Procurement | Procurement Policies | Extend Maaden procurement policies to the JV | Fathima Mahomed | Not Started | 2026-04-05 | 14 | 2026-04-19 | 0% | 0%
Operational readiness | HR | Determine secondees positions | Determine which positions will be filled by secondees | Mohammed Al-Hamed | Not Started | 2026-03-13 | 7 | 2026-03-20 | 0% | 0%
Operational readiness | HR | Secondee nomination and mobilization | Obtain nomination from JV GM and mobilize secondees | Rene Thumbran | Not Started | 2026-07-27 | 7 | 2026-08-03 | 0% | 0%
Operational readiness | HR | Secondees performance KPIs definition | Define main JV secondees performance KPIs | Rene Thumbran | Not Started | 2026-03-20 | 14 | 2026-04-03 | 0% | 0%
Operational readiness | HR | HR Policies & Processes Framework and Setup | Set up HR processes, policies and systems for JV | Rene Thumbran | Not Started | 2026-03-20 | 14 | 2026-04-03 | 0% | 0%
Operational readiness | HSSE | HSSE Policy & Process Framework | Define JV's HSE policies, procedures and systems requirements | Faraj Al Dossary | Not Started | 2026-03-04 | 14 | 2026-03-18 | 0% | 0%
Operational readiness | HSSE | HSSE Policy & Process Setup | Set up HSE processes, policies and systems for JV (e.g. incident reporting system) | Faraj Al Dossary | Not Started | 2026-05-19 | 14 | 2026-06-02 | 0% | 0%
Operational readiness | HSSE | Emergency Response Plan | Develop emergency response plan | Faraj Al Dossary | Not Started | 2026-05-19 | 14 | 2026-06-02 | 0% | 0%
Operational readiness | HSSE | Field HSSE plan | Develop HSSE plan for exploration activities | Faraj Al Dossary | Not Started | 2026-05-19 | 14 | 2026-06-02 | 0% | 0%
Operational readiness | HSSE | PPE procurement request | Request personal protective equipment for relevant day-1 staff | Faraj Al Dossary | Not Started | 2026-07-27 | 7 | 2026-08-03 | 0% | 0%
Operational readiness | Comms | Stakeholder comms plan | Develop external stakeholder communications plan | Susan Parker | Not Started | 2026-04-19 | 14 | 2026-05-03 | 0% | 0%
Operational readiness | Comms | Press release (Day-1) | Prepare and publish press-release for launch announcement | Susan Parker | Not Started | 2026-05-12 | 7 | 2026-05-19 | 0% | 0%
Operational readiness | Comms | Government stakeholder briefing | Brief key government stakeholders | Susan Parker | Not Started | 2026-05-12 | 7 | 2026-05-19 | 0% | 0%
Operational readiness | Facilities | JV Office Setup | Define permanent HQ location setup plan, and secure physical office space (e.g. sign leasing contract if needed) | Raoof Madathil | Not Started | 2026-07-27 | 14 | 2026-08-10 | 0% | 0%
Formulas:
Start date = MIN([Start date, row below]:G13)
Start date = [End date, row above]
End date = MAX([End date, row below]:I13)
End date = [Start date]+[Duration]
Target Completion (%) = IFERROR(MAX(0,MIN(1,(TODAY()-[Start date])/([End date]-[Start date]))),"")

## Data Validation List (hidden)
Critical | Status
Yes | Not Started
No | Delayed
On-track
Completed