## Cover
Title | Project Crystal - JV Day 1 Readiness Plan
Description | All actions required to achieve JV Day-1 operational readiness
Date | 2026-03-10

## Summary
REQUIREMENTS BY OWNER | 38 | 14 | 23 | 1 | REQUIREMENTS BY CATEGORY | 105 | 81 | 23 | 1
Owner | Total | Completed | On-track | Delayed | Workstream | Total | Not started | On-track | Delayed
Hassen Moolla | 9 | 3 | 5 | 1 | Budget and BP | 6 | 4 | 2 | 0
Muddassar Khan | 10 | 5 | 5 | 0 | TSA | 4 | 1 | 3 | 0
Ramesh Murugesan | 2 | 1 | 1 | 0 | GSA | 6 | 2 | 3 | 1
Mawiyah Alqaed | 1 | 1 | 0 | 0 | DoA | 2 | 1 | 1 | 0
Aseel Alnafea | 3 | 0 | 3 | 0 | Secondment | 4 | 2 | 2 | 0
Rene Thumbran | 2 | 0 | 2 | 0 | SHA documentation | 8 | 2 | 6 | 0
Mohammed Al-Hamed | 3 | 1 | 2 | 0 | Corporate approval | 4 | 2 | 2 | 0
Omar Jabart | 2 | 1 | 1 | 0 | Governance | 19 | 19 | 0 | 0
Faraj Al Dossary | 1 | 0 | 1 | 0 | Legal | 6 | 6 | 0 | 0
Abdulrahman Abdullah Al-zahrani | 0 | 0 | 0 | 0 | GR | 4 | 4 | 0 | 0
Fathima Mahomed | 1 | 0 | 1 | 0 | HR | 6 | 5 | 1 | 0
Muddassar/ Mohammed | 0 | 0 | 0 | 0 | HSSE | 6 | 5 | 1 | 0
Susan Parker | 0 | 0 | 0 | 0 | Finance | 10 | 10 | 0 | 0
Owen Hatton | 2 | 2 | 0 | 0 | IT | 12 | 11 | 1 | 0
Muddassar | 2 | 0 | 2 | 0 | Procurement | 4 | 3 | 1 | 0
Aramco | 0 | 0 | 0 | 0 | Comms | 3 | 3 | 0 | 0
Maaden and Aramco CEOs | 0 | 0 | 0 | 0 | Facilities | 1 | 1 | 0 | 0
Abdullah Alzamil | 0 | 0 | 0 | 0
Karim Mehboob | 0 | 0 | 0 | 0
Marwan Sutan | 0 | 0 | 0 | 0
Raud Alsuwailem | 0 | 0 | 0 | 0
Governance dept | 0 | 0 | 0 | 0
Raoof Madathil | 0 | 0 | 0 | 0
2026-03-09

## JV Readiness Plan
PROJECT CRYSTAL - JV DAY-1 READINESS PLAN | [6 empty] | Day-1 target date | 2026-08-26
Workstream | Category | Requirement | Action | Owner | Status | Start date | Duration | End date | Target Completion (%) | Actual Completion (%) | Notes
| Budget and Business Plan |  |  |  |  | 2026-02-01 | 58 | 2026-03-31
SHA | Budget and BP | Budget & BP Roles & Data Sources | Clarify roles and responsibilities across Maaden finance and technical teams. Define who provides what, sources of information, and internal points of contact for each workstream. | Hassen Moolla | Completed | 2026-02-01 | 14 | 2026-02-15 | 100% | 100%
SHA | Budget and BP | Budget and BP Inputs & Assumptions | Identify the full list of inputs and assumptions required to build the model. Define sources and providers for each item, and set deadlines for delivery. | Hassen Moolla | Completed | 2026-02-15 | 18 | 2026-03-05 | 100% | 100% | The full list of inputs and assumptions has been identified (Maaden view) and sources and providers have been defined. Next step is to build the model.
SHA | Budget and BP | 5-Year Exploration Plan | Develop 5-year Exploration Plan (2026-2030) | Owen Hatton | Completed | 2026-02-15 | 18 | 2026-03-05 | 100% | 100% | Working program has been prepared and approved by Maaden leadership. Granular view available for 2026 and forecast covering 2027–2030. Available to be shared upon request.
SHA | Budget and BP | JV Day-1 Org Chart | Finalize the Day-1 organization structure (confirm minimal technical staff requirements, including HSSE) | Mohammed Al-Hamed | Completed | 2026-02-18 | 14 | 2026-03-04 | 100% | 100% | Day-1 organization structure has been finalized and is ready to be shared.
SHA | Budget and BP | Build Draft BP Model | Construct the financial and operational model based on the defined inputs, assumptions, and agreed structure. Ensure formulas are robust and the model is auditable. | Hassen Moolla | On-track | 2026-03-05 | 7 | 2026-03-12 | 71.43% | 70% | Model development is currently being executed. First draft to be delivered by Maaden by 12 March 2026.
SHA | Budget and BP | Validate BP with Key Maaden Stakeholders | ². Incorporate feedback and resolve any open items. | Hassen Moolla | Not Started | 2026-03-12 | 3 | 2026-03-15 | 0% | 0%
SHA | Budget and BP | Align on BP template | Maaden and Aramco to align on format/templates of final BP deliverables | Hassen Moolla | On-track | 2026-03-08 | 4 | 2026-03-12 | 50% | 50%
SHA | Budget and BP | Package BP into Final Deliverable | Develop final BP deliverables as per template defined | Hassen Moolla | Not Started | 2026-03-15 | 7 | 2026-03-22 | 0% | 0%
SHA | Budget and BP | BP Final Deliverable validation | Validate final deliverables | Mohammed Al-Hamed | Not Started | 2026-03-22 | 2 | 2026-03-24 | 0% | 0%
SHA | Budget and BP | Aramco Feedback on BP & Update | Share the finalized BP with Aramco for review. Collect feedback, incorporate agreed changes, and lock the final version for approval | Mohammed Al-Hamed | Not Started | 2026-03-24 | 7 | 2026-03-31 | 0% | 0%
| TSA |  |  |  |  | 2026-02-01 | 56 | 2026-03-29
SHA | TSA | TSA Technical Services Catalogue | Develop the catalogue of technical services to be provided by Maaden to the JV under the TSA, identify what services are to be provided by 3d parties | Owen Hatton | Completed | 2026-02-01 | 11 | 2026-02-12 | 100% | 100%
SHA | TSA | TSA Charge-out Rate Methodology | Define the pricing methodology: establish the approach and basis for pricing each category of services (e.g., cost-plus, market benchmark, fixed fee) | Hassen Moolla | Completed | 2026-02-12 | 24 | 2026-03-08 | 100% | 100% | Initial approach has been defined. To be reviewed and agreed with workstream leader during the week of 8–15 March 2026.
SHA | TSA | TSA Charge-out Rates Determination | Apply the agreed pricing methodology to determine the applicable rates for each service in the catalogue | Hassen Moolla | On-track | 2026-03-08 | 7 | 2026-03-15 | 28.57% | 30% | To be initiated following review and agreement of the pricing methodology with workstream leaders. Target completion by 15 March 2026.
SHA | TSA | TSA Governance structure | Define TSA governance structure and process: how TSA services are requested, approved, monitored, billed, paid, accounted (TSA management process) | Muddassar | On-track | 2026-03-04 | 14 | 2026-03-18 | 42.86% | 30% | Aramco TSA has been reviewed and comments shared with legal. On Maaden TSA, concept is being developed; first internal discussions with Maaden project leadership scheduled for early next week.
SHA | TSA | TSA Legal framework | Finalize the TSA legal framework: draft and agree on the legal terms and conditions governing the provision of services, including scope, performance standards, liability, and termination provisions | Aseel Alnafea | On-track | 2026-03-08 | 14 | 2026-03-22 | 14.29% | 15%
SHA | TSA | Aramco Feedback on TSA & Update | Share the finalized TSA version with Aramco for review. Collect feedback, incorporate agreed changes, and lock the final version for approval. | Muddassar Khan | Not Started | 2026-03-22 | 7 | 2026-03-29 | 0% | 0%
| GSA |  |  |  |  | 2026-02-01 | 56 | 2026-03-29
SHA | GSA | GSA Catalogue of services | Develop the catalogue of services to be provided by Maaden to the JV under the GSA | Hassen Moolla | Delayed | 2026-02-01 | 35 | 2026-03-08 | 100% | 80% | Catalogue has been developed and partially validated by workstream leaders. Target to finalise validation by 10 March 2026.
SHA | GSA | GSA Charge-out Rate Methodology | Define the pricing methodology: establish the approach and basis for pricing each category of services (e.g., cost-plus, market benchmark, fixed fee) | Hassen Moolla | On-track | 2026-02-16 | 24 | 2026-03-12 | 91.67% | 80% | Initial approach has been defined. To be reviewed and agreed with workstream leaders during the week of 8–15 March 2026.
SHA | GSA | GSA Charge-out Rates Determination | Apply the agreed pricing methodology to determine the applicable rates for each service in the catalogue | Hassen Moolla | Not Started | 2026-03-12 | 7 | 2026-03-19 | 0% | 0%
SHA | GSA | GSA Governance structure | Define GSA governance structure and process : how GSA services are requested, approved, monitored, billed, paid, accounted (GSA management process) | Muddassar | On-track | 2026-03-04 | 14 | 2026-03-18 | 42.86% | 30% | On Maaden GSA, concept is being developed; first internal discussions with Maaden project leadership scheduled for early next week.
SHA | GSA | GSA Legal framework | Finalize the GSA legal framework: draft and agree on the legal terms and conditions governing the provision of services, including scope, performance standards, liability, and termination provisions | Aseel Alnafea | On-track | 2026-03-08 | 14 | 2026-03-22 | 14.29% | 15%
SHA | GSA | Aramco Feedback on GSA & Update | Share the finalized TSA version with Aramco for review. Collect feedback, incorporate agreed changes, and lock the final version for approval | Muddassar Khan | Not Started | 2026-03-22 | 7 | 2026-03-29 | 0% | 0% | STILL OPEN. Schedule 13 is completely empty. Each party needs to disclose their existing competing businesses. This is referenced in Clause 20.1(a)(i).STILL OPEN. Schedule 14 is completely empty. The funding notice templates need to be developed. Plus, the distinction between 'Form of Funding Notices' and 'Funding Request Notice template' is unclear in the SHA.
| DoA |  |  |  |  | 2026-02-15 | 37 | 2026-03-24
SHA | DoA | Shareholders DoAs reference | Obtain reference governance framework, obtain Maaden's existing Authority Matrix and Aramco's governance frameworks as benchmarks for the JV | Mawiyah Alqaed | Completed | 2026-02-24 | 9 | 2026-03-05 | 100% | 100%
SHA | DoA | Complete Design of DoA (Shedule 15) | Design the multi-tiered financial approval matrix (incl governance and internal controls) : define approval tiers below Board thresholds across CAPEX, OPEX, contracts, procurement, HR, litigation, treasury, and asset management, aligned with SHA | Omar Jabart | On-track | 2026-02-15 | 30 | 2026-03-17 | 76.67% | 80% | Mar 9th: Draft prepared; under review by Effat
SHA | DoA | Aramco Feedback on DoA & Update | Share the finalized DoA version with Aramco for review. Collect feedback, incorporate agreed changes, and lock the final version for approval | Muddassar/ Mohammed | Not Started | 2026-03-17 | 7 | 2026-03-24 | 0% | 0%
| Secondment |  |  |  |  | 2026-02-01 | 62 | 2026-04-04
SHA | Secondment | Secondment framework | Develop secondment framework agreement (duration, cost basis, reporting lines, benefits) | Rene Thumbran | On-track | 2026-02-01 | 40 | 2026-03-13 | 92.5% | 80% | Standard master framework
SHA | Secondment | Secondment Agreement Allocation Methodology | Define cost allocation methodology and determine cost rates for secondees | Rene Thumbran | On-track | 2026-02-02 | 40 | 2026-03-14 | 90% | 80%
SHA | Secondment | JV Secondment Agreement draft | Draft JV secondment agreement | Aseel Alnafea | Not Started | 2026-03-14 | 14 | 2026-03-28 | 0% | 0% | with support of Rene Thumbran
SHA | Secondment | Aramco Feedback on Secondment Agreement & Update | Share the finalized Secondment Agreement with Aramco for review. Collect feedback, incorporate agreed changes, and lock the final version for approval | Muddassar/ Mohammed | Not Started | 2026-03-28 | 7 | 2026-04-04 | 0% | 0%
| SHA documentation |  |  |  |  | 2026-02-19 | 62 | 2026-04-22
SHA | SHA documentation | SHA Sch.11 Guarantee for Permitted Transfers | Agree Form of Guarantee for Permitted Transfers (Schedule 11) | Muddassar Khan | On-track | 2026-02-19 | 20 | 2026-03-11 | 95%
SHA | SHA documentation | SHA Sch.12 Form of the Agreement | Finalize Form of Shareholder Services Agreement (Schedule 12) | Muddassar Khan | Not Started | 2026-03-18 | 7 | 2026-03-25 | 0% |  | STILL OPEN. What exactly is this form? We understand GSA is a separament document, correct?
SHA | SHA documentation | SHA Sch.14 Competing business disclosure | Complete existing competing businesses disclosure (Schedule 14) (action also required for aramco) | Aseel Alnafea | On-track | 2026-02-24 | 14 | 2026-03-10 | 100% |  | STILL OPEN. Schedule 13 is completely empty. Each party needs to disclose their existing competing businesses. This is referenced in Clause 20.1(a)(i).
SHA | SHA documentation | SHA Sch.15 Funding Notices | Develop Form of Funding Notices, and standard Funding Request Notice template (Schedule 15) and share with Legal for incorporation into SHA | Hassen Moolla | On-track | 2026-02-19 | 20 | 2026-03-11 | 95% | 95% | Hassen to share with Legal
SHA | SHA documentation | SHA Sch.2 Area of Interest and Transition Zone | Provide all Area of Interest and Transition Zone maps and coordinates (Schedule 2) and share with Legal for incorporation into SHA | Mohammed Al-Hamed | On-track | 2026-02-19 | 20 | 2026-03-11 | 95% | 95% | Map in Part 1 is included, but all coordinate fields and the Transition Zone map remain as placeholders. Footnote 5 explicitly asks MDN to confirm.
SHA | SHA documentation | Exploration License Assignment Agreeement | Finalize Exploration License Assignment Agreeement | Muddassar Khan | On-track | 2026-02-19 | 42 | 2026-04-02 | 45.24% |  | Is this a separate agreement, or should it be a SHA section/schedule? Is this the same as Exploration Services Agreement?
SHA | SHA documentation | Exploration Services Agreement | Finalize Exploration Services Agreement | Muddassar Khan | On-track | 2026-02-19 | 42 | 2026-04-02 | 45.24% |  | Confirm with Aramco/Legal if this is Maaden's Technical Service Agreements or something else. Note: CVA validated full catalogue of technical services with Mohammed/Owen, next step: determine prices/SLAs with Abulrahman and Hassen
SHA | SHA documentation | Aramco Feedback on SHA pack & Update | Share the final SHA documentation with Aramco for review. Collect feedback, incorporate agreed changes, and lock the final version for approval | Muddassar/ Mohammed | Not Started | 2026-04-02 | 20 | 2026-04-22 | 0% | 0%
| Corporate approval |  |  |  |  | 2026-02-08 | 95 | 2026-05-14
SHA | Corporate approval | Maaden IC | Prepare material and obtain approval at Maaden Investment Committee meeting | Muddassar Khan | Completed | 2026-02-08 | 1 | 2026-02-09 | 100% | 100%
SHA | Corporate approval | Maaden ExCom | Prepare material and obtain approval at Maaden Excom meeting (Feb 17) | Muddassar Khan | Completed | 2026-02-17 | 1 | 2026-02-18 | 100% | 100%
SHA | Corporate approval | Maaden BoD | Prepare material and obtain approval at BoD meeting (Mar 5) | Muddassar Khan | Completed | 2026-03-05 | 1 | 2026-03-06 | 100% | 100% | Incorporation resolution, Properly executed according to each Shareholder's internal corporate governance requirements, Likely notarized and legalized/apostilled for use in MOC
SHA | Corporate approval | 365-Day Implementation Plan Draft | Draft 365 Day Implementation Plan | Muddassar Khan | Completed | 2026-02-23 | 14 | 2026-03-09 | 100% | 100% | Draft reviewed by Mohammed and Muddassar on Mar 9th
SHA | Corporate approval | 365-Day Implementation Plan (Final) | Review and share the finalized Plan with Aramco for review. Collect feedback, incorporate agreed changes, and lock the final version for approval | Muddassar Khan | On-track | 2026-03-09 | 7 | 2026-03-16 | 14.29% | 25%
SHA | Corporate approval | 5-year Implementation Plan Draft | Draft JV Long-term Implementation Plan (key milestones) | Muddassar Khan | Completed | 2026-02-23 | 14 | 2026-03-09 | 100% | 100% | Draft reviewed by Mohammed and Muddassar on Mar 9th
SHA | Corporate approval | 5-year Implementation Plan (Final) | Review and share the finalized Plan with Aramco for review. Collect feedback, incorporate agreed changes, and lock the final version for approval | Muddassar Khan | On-track | 2026-03-09 | 7 | 2026-03-16 | 14.29% | 25%
SHA | Corporate approval | Board of Directors Aramco | Obtain approval at BoD meeting (mid-May) | Aramco | Not Started | 2026-05-08 | 1 | 2026-05-09 | 0% | 0%
SHA | Corporate approval | SHA signed by both Shareholders | Sign Shareholder Agreement | Maaden and Aramco CEOs | Not Started | 2026-05-09 | 5 | 2026-05-14 | 0% | 0% | Need to confirme timeline and what is prerequisite for signing and what can be handled as CP. This is the final deliverable. Potential key blockers: multiple empty schedules, numerous 'Note to Draft' items, outstanding commercial terms
| Entity Formation |  |  |  |  | 2026-03-01 | 143 | 2026-07-22
Entity Formation | Governance | Power of Attorney (PoA) | Issue legalized power of attorney authorizing Kingdom representatives before MOC and SBC (action also required for Aramco) | Omar Jabart | Completed | 2026-03-01 | 14 | 2026-03-15 | 64.29% |  | authorize representatives before MOC and SBC (Maaden issued, Aramco pending), PoA was issued for AshLaw, a question to Aramco about their PoA
Entity Formation | Governance | Trade name reservation | Submit reservation of Trade name with Saudi Business Center (SBC), and obtain name approval from MOC | Aseel Alnafea | Not Started | 2026-03-15 | 7 | 2026-03-22 | 0% | 0% | AshLaw 24 hours (in MPP ithe timeline is 5-10 business days) A commercial name reservation remains valid for only 60 days but may be renewed prior to expiry.
Entity Formation | Governance | Constitutional documents | Gather constitutional documents and Financial Statements (e.g., certificate of incorporation and articles (or equivalent) and audited financial statements of each Shareholder | Mawiyah Alqaed | Not Started | 2026-03-15 | 14 | 2026-03-29 | 0% | 0% | Based on the SHA document, for MOC/SBC approval of AoA
Entity Formation | Governance | Board members nomination | Both shareholders nominate board members | Maaden and Aramco CEOs | Not Started | 2026-04-02 | 7 | 2026-04-09 | 0% | 0%
Entity Formation | Governance | Initial Board remuneration | Define initial remuneration for Board Memebrs (action also required for Aramco) | Mawiyah Alqaed | Not Started | 2026-04-09 | 14 | 2026-04-23 | 0% |  | To be completed once the board member nomination list is finalised.
Entity Formation | Governance | Board members’ and GM information | Gather - from each board member and GM - a copy of passport/ID and contact information for MoC (action also required for Aramco) | Mawiyah Alqaed | Not Started | 2026-04-02 | 14 | 2026-04-16 | 0% | 0% | Source: Steps Plan - company incorporation
Entity Formation | Governance | Details of the ultimate beneficiary(ies) for MOC | Gather information of the ultimate beneficiaries for Ministry of Commerce | Mawiyah Alqaed | Not Started | 2026-04-30 | 14 | 2026-05-14 | 0% | 0% | For and Aramco, since it is a listed joint stock company, the following information would be required for the natural person having the authority to represent in general assemblies of companies owned by Maaden: • Full name. • ID number. • Date and place of birth. • Nationality. • National address. • Phone number. • Email address (if any). Ultamate Benifiacry is on Tadawul for Maaden and Aramco
Entity Formation | Governance | Board members/GM appointment consent | Board members and GM to approve their appointment - completed via Absher digital system (action also required for Aramco) | Mawiyah Alqaed | Not Started | 2026-04-02 | 14 | 2026-04-16 | 0% | 0% | For KSA nationals/residents, approval can be made: •electronically through a onetime password sent to the phone number registered with the KSA authorities, which can be shared with CC at the relevant time; or •in writing by signing a consent letter and authenticating the signature before: (i) the Chamber of Commerce; (ii) MOC; or (iii) a KSA licensed bank. • For non-KSA nationals/residents, approval can be made in writing by signing a consent letter and authenticating the signature by apostille or notarization and legalization up to the level of the KSA embassy and the Ministry of Foreign Affairs.
Entity Formation | Legal | GAC no-notification application form | Prepare GAC no-notification application form to be submitted to the GAC | Aseel Alnafea | Not Started | 2026-04-15 | 7 | 2026-04-22 | 0% | 0% | Critical path , prior to AoA notarization and CR issuing. waiting period up to 90 days, it will require a significant pack of documents: signed SHA, transaction description, copies of CR, AoA of the mother companies, org chart of the mother companies,audited finance reports…
Entity Formation | Legal | GAC no-notification economic report | Submit GAC no-notification economic report | Aseel Alnafea | Not Started | 2026-04-15 | 7 | 2026-04-22 | 0% | 0%
Entity Formation | Legal | GAC approval | Apply for and receive all required antitrust approvals (including GAC confirmation of non-applicability) | Aseel Alnafea | Not Started | 2026-05-14 | 60 | 2026-07-13 | 0% | 0%
Entity Formation | Governance | Board appointment Shareholders resolutions | Each Shareholder formally approves the appointment of their nominated Directors (action also required for Aramco) | Mawiyah Alqaed | Not Started | 2026-04-02 | 14 | 2026-04-16 | 0% | 0% | Schedule 12, Part 2, paragraph 3.1 requires that at least three (3) Business Days prior to the Commencement Date, each Shareholder must deliver to the other a written Shareholders' resolution approving the appointment of their respective Directors in accordance with Clause 6.
Entity Formation | Governance | AoA drafting | Draft AoA incorporating SHA terms and get shareholders approval | Omar Jabart | Not Started | 2026-04-15 | 21 | 2026-05-06 | 0% | 0% | with support of Aseel Alnafea /AshLaw (paragraph 2.1.2(d) of Part 2, Schedule 12) Arabic, per MOC template; Led by Mawiyah Alqaed/Aramco Governance with support of Aseel Alnafea / Aramco Legal
Entity Formation | Governance | AoA approval | Submit AoA through SBC Portal (MOC) for MOC approval | Omar Jabart | Not Started | 2026-05-06 | 21 | 2026-05-27 | 0% | 0% | 2-3 weeks for MOC review. At the Commencement date SHaholders exchange signed SHA and transactional documents (Secondment Agreement, GSAs, TSAs, ESA) On the Commencement Date, the AoA are signed before MOC/SBC, shares are issued, and the entity comes into existence. The directors named in those pre-completion resolutions are effectively the initial directors.
Entity Formation | Legal | AoA signing | Sign AoA before MOC/SBC official (via SBC portal) (with participation of Aramco) | Aseel Alnafea | Not Started | 2026-07-13 | 1 | 2026-07-14 | 0% | 0% | At the Commencement date SHaholders exchange signed SHA and transactional documents (Secondment Agreement, GSAs, TSAs, ESA)On the Commencement Date, the AoA are signed before MOC/SBC, shares are issued, and the entity comes into existence. The directors named in those pre-completion resolutions are effectively the initial directors.
Entity Formation | Governance | AoA issuing | Complete payment of the MOC application and publication fees, Deliver Articles of Association issued electronically via the SBC portal | Mawiyah Alqaed | Not Started | 2026-07-14 | 2 | 2026-07-16 | 0% | 0% | with support of Maaden GR (Abdulrahman Abdullah Al-zahrani) Payment of the relevant application fees must be made through SADAD within a period to be specified in an invoice to be issued by MOC; otherwise, the application will be cancelled automatically. MOC typically publishes the articles of association within 24 hours after the payment has been made.
Entity Formation | Governance | Maaden Board Members Registration with MOC | Formally register all Maaden directors with MOC | Omar Jabart | Not Started | 2026-07-16 | 3 | 2026-07-19 | 0% | 0%
Entity Formation | Governance | Aramco Board Members Registration with MOC | Formally register all Aramco directors with MOC | Aramco | Not Started | 2026-07-16 | 3 | 2026-07-19 | 0% | 0%
Entity Formation | Governance | Commercial Registration (CR) | Obtain CR from Ministry of Commerce | Omar Jabart | Not Started | 2026-07-19 | 3 | 2026-07-22 | 0% | 0% | or Aramco Governance depending on AoA submission
| Post-formation registration |  |  |  |  | 2026-07-22 | 14 | 2026-08-05
Post-formation registration | GR | Chamber of Commerce registration | Register with local Chamber of Commerce | Abdulrahman Abdullah Al-zahrani | Not Started | 2026-07-22 | 7 | 2026-07-29 | 0% | 0%
Post-formation registration | Legal | ZAKAT, TAX and Customs registration | Register with the ZAKAT, Tax and Customs Authority | Abdullah Alzamil | Not Started | 2026-07-22 | 7 | 2026-07-29 | 0% | 0% | Required for invoicing
Post-formation registration | Legal | VAT registration | Register for VAT with ZATCA | Abdullah Alzamil | Not Started | 2026-07-22 | 14 | 2026-08-05 | 0% | 0%
Post-formation registration | GR | GOSI registration | Register with General Organization for Social Insurance (GOSI) | Abdulrahman Abdullah Al-zahrani | Not Started | 2026-07-22 | 7 | 2026-07-29 | 0% | 0% | Required before hiring
Post-formation registration | HR | MHRSD registration | Register with Ministry of Human Resources (MHRSD) | Rene Thumbran | Not Started | 2026-07-22 | 7 | 2026-07-29 | 0% | 0% | Labor law compliance
Post-formation registration | GR | Saudi Post Registration | Registration with the Saudi Post Office | Abdulrahman Abdullah Al-zahrani | Not Started | 2026-07-22 | 7 | 2026-07-29 | 0% | 0%
Post-formation registration | GR | Municipality License | Obtain a municipality License from Ministry of Municipal and Rural Affairs | Abdulrahman Abdullah Al-zahrani | Not Started | 2026-07-22 | 14 | 2026-08-05 | 0% | 0%
Post-formation registration | HR | Nitaqat classification | Obtain initial Saudization classification | Rene Thumbran | Not Started | 2026-07-22 | 14 | 2026-08-05 | 0% | 0%
Post-formation registration | HSSE | Civil Defence Certificate | Obtain a Civil Defence Certificate, as necessary | Faraj Al Dossary | Not Started | 2026-07-22 | 14 | 2026-08-05 | 0% | 0%
| Corporate Governance Setup |  |  |  |  | 2026-05-14 | 97 | 2026-08-19
Corporate Governance Setup | Governance | BoD Charter | Develop BoD Charter (incl. board composition, committees, authority matrices, voting & veto rights, exec management governance, performance assessment) | Mawiyah Alqaed | Not Started | 2026-05-14 | 21 | 2026-06-04 | 0% | 0%
Corporate Governance Setup | Governance | Board of Directors on-boarding | Prepare on-boarding documentation for JV Board of Directors | Raud Alsuwailem | Not Started | 2026-06-04 | 14 | 2026-06-18 | 0% | 0%
Corporate Governance Setup | Governance | Shareholders Resolution (General Assembly) | Shareholders undertake all resolutions (by unanimous written circular resolution or General Assembly) required to give effect to SHA terms (action also required for Aramco) | Mawiyah Alqaed | Not Started | 2026-07-15 | 7 | 2026-07-22 | 0% | 0% | Per SHA Clause 3.1(b)
Corporate Governance Setup | Governance | Inaugural Board meeting | Prepare and conduct first Board meeting and approve foundational resolutions (e.g. company accession) | Mawiyah Alqaed | Not Started | 2026-07-22 | 7 | 2026-07-29 | 0% | 0% | with support of Board Secretary First Board Meeting — Must Resolve: Appoint Management TeamCEO, CFO, GM of Exploration, Financial Controller Open bank account With KSA-licensed bank Ratify Initial Budget and Business Plan Adopt Related Agreements GSAs, TSA, Secondment, Exploration Services Adopt Company policies HR, finance, procurement, etc.Adopt Initial Authority MatrixDelegation of authority framework
Corporate Governance Setup | Governance | Executive management transition plan | Develop executive management transition support plan to support smooth handover from setup phase to operational governance | Governance dept | Not Started | 2026-07-29 | 21 | 2026-08-19 | 0% | 0% | First Board Meeting — Must Resolve: Appoint Management TeamCEO, CFO, GM of Exploration, Financial Controller Open bank account With KSA-licensed bank Ratify Initial Budget and Business Plan Adopt Related Agreements GSAs, TSA, Secondment, Exploration Services Adopt Company policies HR, finance, procurement, etc.Adopt Initial Authority MatrixDelegation of authority framework
| Operational readiness |  |  |  |  | 2026-02-17 | 190 | 2026-08-26
Operational readiness | Finance | Financial Policy Manual | Identify policy required for JV to operate and develop Finance Policy Manual | Hassen Moolla | Not Started | 2026-04-05 | 21 | 2026-04-26 | 0% | 0% | Leverage Maaden accounting policy manual, maaden exploration procedure manual to be adopted by JV,
Operational readiness | Finance | JV Financial KPIs | Define Finance KPIs & monitor main performance measurement indicators | Hassen Moolla | Not Started | 2026-04-05 | 14 | 2026-04-19 | 0% | 0%
Operational readiness | Finance | Financial reporting templates | Define standard monthly /quarterly financial report templates (including BoD, shareholders) and align with Aramco CFO | Hassen Moolla | Not Started | 2026-04-19 | 14 | 2026-05-03 | 0% | 0%
Operational readiness | Finance | Auditing principles | Agree on external auditor selection criteria and process, define audit committee role, and confirm audit timeline for Year 1 | Karim Mehboob | Not Started | 2026-04-05 | 14 | 2026-04-19 | 0% | 0%
Operational readiness | Finance | External auditor selection | Identify and shortlist external auditors, define scope of audit, present recommendation to Board for approval at inaugural meeting | Karim Mehboob | Not Started | 2026-04-19 | 60 | 2026-06-18 | 0% | 0%
Operational readiness | Finance | Initial Insurance protection | Identify and procure insurance coverage for the JV (D&O liability, general liability, professional indemnity, property/equipment insurance for exploration activities) | Hassen Moolla | Not Started | 2026-06-10 | 14 | 2026-06-24 | 0% | 0%
Operational readiness | Finance | Corporate bank accounts | Open bank accounts | Marwan Sutan | Not Started | 2026-07-22 | 21 | 2026-08-12 | 0% | 0% | Requires Commercial Registration (CR), Article of Association (AoA), Board Resolution, Board Bank Delegation of Authority, Bank KYC process → 2-4 weeks typically
Operational readiness | Finance | Bank signatory authorization | Register authorized signatories | Marwan Sutan | Not Started | 2026-07-22 | 7 | 2026-07-29 | 0% | 0% | Need GM appointed,
Operational readiness | Finance | Cash call schedule Year 1 | Define quarterly funding schedule | Hassen Moolla | Not Started | 2026-03-15 | 7 | 2026-03-22 | 0% | 0%
Operational readiness | Finance | Initial capital contribution | Initial cash call from shareholders | Mohammed Al-Hamed | Not Started | 2026-08-12 | 14 | 2026-08-26 | 0% | 0% | not later than 15 business days after the Commencement Date
Operational readiness | IT | IT Systems requirements | Identify all systems needed for JV | Ramesh Murugesan | Completed | 2026-02-17 | 21 | 2026-03-10 | 100% | 100%
Operational readiness | IT | IT Work scope | Scoping and requirement documentation | Ramesh Murugesan | On-track | 2026-03-10 | 14 | 2026-03-24 | 0% | 0% | ERP, Procurement (subsystems) - email sent to Adel as per Ramesh direction
Operational readiness | IT | Shareholders' IT Alignment | Prepare and conduct workshop with Aramco IT to showcase Maaden systems capabilities and agree on IT strategy | Ramesh Murugesan | Not Started | 2026-03-24 | 30 | 2026-04-23 | 0% | 0%
Operational readiness | IT | IT systems Implementation | Implement systems (configuration, training, testing, deployment) | Ramesh Murugesan | Not Started | 2026-03-24 | 90 | 2026-06-22 | 0% | 0%
Operational readiness | IT | IT Access Rights Assigned to JV Users | Grant relevant system access to end users | Ramesh Murugesan | Not Started | 2026-06-22 | 3 | 2026-06-25 | 0% | 0%
Operational readiness | IT | Chart of Accounts configuration | Load CoA in ERP | Ramesh Murugesan | Not Started | 2026-06-25 | 7 | 2026-07-02 | 0% | 0%
Operational readiness | IT | JV New IT Systems Subscriptions & Licences | Acquire / subscribe to systems needed for JV operations (not available through shareholders) | Ramesh Murugesan | Not Started | 2026-03-24 | 60 | 2026-05-23 | 0% | 0%
Operational readiness | IT | IT Systems training | Prepare and run training sessions with JV employees on relevant systems and processes | Ramesh Murugesan | Not Started | 2026-07-22 | 14 | 2026-08-05 | 0% | 0%
Operational readiness | IT | Cybersecurity training | Prepare and run cybersecurity training sessions with day-1 staff | Ramesh Murugesan | Not Started | 2026-07-22 | 14 | 2026-08-05 | 0% | 0%
Operational readiness | IT | JV Email & Account Setup | Register JV email domain (if any) and create email accounts for Day-1 staff | Ramesh Murugesan | Not Started | 2026-07-22 | 7 | 2026-07-29 | 0% | 0% | Need to confirm if there will be new email domains
Operational readiness | IT | Laptops/computers | Provide laptops and mobile phones for day-1 staff | Ramesh Murugesan | Not Started | 2026-05-12 | 60 | 2026-07-11 | 0% | 0%
Operational readiness | IT | Network infrastructure setup | Set up network infrastructure and internet (switches, firewall, routers) | Ramesh Murugesan | Not Started | 2026-05-12 | 60 | 2026-07-11 | 0% | 0%
Operational readiness | IT | Aramco Data migration plan | Manage and oversee data migration plan for all relevant data | Ramesh Murugesan | Not Started | 2026-07-22 | 14 | 2026-08-05 | 0% | 0%
Operational readiness | Procurement | Maaden Contracts Capacity Review | Assess the capacity of Maaden's existing contracts against the JV's projected demand, based on the JV Technical Work Program | Fathima Mahomed | On-track | 2026-03-09 | 21 | 2026-03-30 | 4.762% | 0% | 2026 technical work program is a prerequisite
Operational readiness | Procurement | JV Procurement Plan | Develop a Procurement Plan to cover scope not addressed by existing contracts, based on the outcomes of the Contract Capacity Review. | Fathima Mahomed | Not Started | 2026-03-30 | 21 | 2026-04-20 | 0% | 0% | A plan on activities- i.e what services/materials etc is required from the operational team - this is a pre-requisite (2026 technical work program )
Operational readiness | Procurement | Procurement Demand Assessment | Estimate procurement activity volumes and define resource requirements to support JV demand | Fathima Mahomed | Not Started | 2026-04-20 | 14 | 2026-05-04 | 0% | 0% | This will depend on the 2026 technical work program and the estinated procurement budget
Operational readiness | Procurement | Procurement Policies | Extend Maaden procurement policies to the JV | Fathima Mahomed | Not Started | 2026-04-05 | 14 | 2026-04-19 | 0% | 0% | This is subject to the operating model and the actions following from this - will this be an addendum to a procedure/policy/document in the JV or will this be an addendum to the Maaden policy /procedure. These decision need to be made by the JV management before this is an action on procurement.
Operational readiness | HR | Determine secondees positions | Determine which positions will be filled by secondees | Mohammed Al-Hamed | On-track | 2026-03-04 | 14 | 2026-03-18 | 42.86% | 50% | Per org design
Operational readiness | HR | Secondee nomination and mobilization | Obtain nomination from JV GM and mobilize secondees | Rene Thumbran | Not Started | 2026-07-22 | 7 | 2026-07-29 | 0% | 0%
Operational readiness | HR | Secondees performance KPIs definition | Define main JV secondees performance KPIs | Rene Thumbran | Not Started | 2026-03-18 | 14 | 2026-04-01 | 0% | 0%
Operational readiness | HR | HR Policies & Processes Framework and Setup | Set up HR processes, policies and systems for JV | Rene Thumbran | Not Started | 2026-03-18 | 14 | 2026-04-01 | 0% | 0%
Operational readiness | HSSE | HSSE Policy & Process Framework | Define JV's HSE policies, procedures and systems requirements | Faraj Al Dossary | On-track | 2026-03-09 | 14 | 2026-03-23 | 7.143%
Operational readiness | HSSE | HSSE Policy & Process Setup | Set up HSE processes, policies and systems for JV (e.g. incident reporting system) | Faraj Al Dossary | Not Started | 2026-05-14 | 14 | 2026-05-28 | 0% | 0%
Operational readiness | HSSE | Emergency Response Plan | Develop emergency response plan | Faraj Al Dossary | Not Started | 2026-05-14 | 14 | 2026-05-28 | 0% | 0%
Operational readiness | HSSE | Field HSSE plan | Develop HSSE plan for exploration activities | Faraj Al Dossary | Not Started | 2026-05-14 | 14 | 2026-05-28 | 0% | 0%
Operational readiness | HSSE | PPE procurement request | Request personal protective equipment for relevant day-1 staff | Faraj Al Dossary | Not Started | 2026-07-22 | 7 | 2026-07-29 | 0% | 0%
Operational readiness | Comms | Stakeholder comms plan | Develop external stakeholder communications plan | Susan Parker | Not Started | 2026-04-19 | 14 | 2026-05-03 | 0% | 0%
Operational readiness | Comms | Press release (Day-1) | Prepare and publish press-release for launch announcement | Susan Parker | Not Started | 2026-05-07 | 7 | 2026-05-14 | 0% | 0% | Both approve
Operational readiness | Comms | Government stakeholder briefing | Brief key government stakeholders | Susan Parker | Not Started | 2026-05-07 | 7 | 2026-05-14 | 0% | 0% | MIMR, etc.
Operational readiness | Facilities | JV Office Setup | Define permanent HQ location setup plan, and secure physical office space (e.g. sign leasing contract if needed) | Raoof Madathil | Not Started | 2026-07-22 | 14 | 2026-08-05 | 0% | 0% | confirm if required - only 7 people fully dedicated to JV
Formulas:
Start date = MIN([Start date, row below]:G14)
Start date = [End date, row above]
End date = MAX([End date, row below]:I14)
End date = [Start date]+[Duration]
Target Completion (%) = IFERROR(MAX(0,MIN(1,(TODAY()-[Start date])/([End date]-[Start date]))),"")

## Pivot Table
Count of Action | Column Labels
Row Labels | Not Started | On-track | Completed | Delayed | Grand Total
Corporate Governance Setup | 5 |  |  |  | 5
Governance | 5 |  |  |  | 5
Entity Formation | 18 |  | 1 |  | 19
Governance | 14 |  | 1 |  | 15
Legal | 4 |  |  |  | 4
Operational readiness | 35 | 4 | 1 |  | 40
IT | 11 | 1 | 1 |  | 13
Finance | 10 |  |  |  | 10
HSSE | 4 | 1 |  |  | 5
Procurement | 3 | 1 |  |  | 4
HR | 3 | 1 |  |  | 4
Comms | 3 |  |  |  | 3
Facilities | 1 |  |  |  | 1
Post-formation registration | 9 |  |  |  | 9
GR | 4 |  |  |  | 4
Legal | 2 |  |  |  | 2
HR | 2 |  |  |  | 2
HSSE | 1 |  |  |  | 1
SHA | 14 | 19 | 12 | 1 | 46
Budget and BP | 4 | 2 | 4 |  | 10
Corporate approval | 2 | 2 | 5 |  | 9
SHA documentation | 2 | 6 |  |  | 8
TSA | 1 | 3 | 2 |  | 6
GSA | 2 | 3 |  | 1 | 6
Secondment | 2 | 2 |  |  | 4
DoA | 1 | 1 | 1 |  | 3
Grand Total | 81 | 23 | 14 | 1 | 119

## Data Validation List (hidden)
Critical | Status
Yes | Not Started
No | Delayed
On-track
Completed